## Dashboard
ESO PROGRAM MANAGEMENT DASHBOARD
Summary Statistics
Metric | Count | Status
Total Activities (Schedule C) | 84
High Priority Items | 10
Upcoming Events | 15
ESO Outreach Activities | 82
Last Updated | 2025-11-06 19:31

## Schedule_Activities
Code | Activity | Tasks | Deliverables | Dependencies | Start date | End date | Reviced date | Unnamed: 8 | Progress | Priority | Unnamed: 11
2.1.6.6 | Due diligence of the shortlisted ESOs | Conduct due diligence of the selected ESOs to determine the legal, financial, programmatic capacity. | Approved Due diligence report, with a Go/ No-Go Decision |  | 2025-08-01 | 2025-08-30 | 2025-09-20 | The regional ESOs did not apply in the first call for proposals which required a scoping visit to understand their uniqueness and refine the RFP. The due diligence is scheduled for 22nd to 26th Sept. | In Progress | High
Work with the FMCS partner on the due diligence report.
|  | Final selection of ESOs to be contracted based on the due diligence report. | Selected ESOs to be contracted
|  | Confirmation with the ESOs on the Go/No- Go decision and the next steps. | ESOs informed about the Go/No- Go decision and the next steps.
2.1.6.7 | Conduct negotiations with selected ESOs, develop work plans. | Discuss draft budgets submitted by ESOs in line with program standards. | 6 Spend plans and work plans |  | 2025-08-18 | 2025-09-17 | 2025-09-30 |  | In Progress | High
Finalize and validate ESO budgets for approval.
2.1.6.8 | Work Plan Development | Jointly develop ESO-specific work plans with clear timelines and milestones. | Approved workplans
Validation & Approval of the final work plans and budgets
2.1.6.8 | Formalize partnerships through signing contracts with 6 additional ESOs onto the 10X Program focused on supporting women entrepreneurs | Prepare partnership frameworks for each of the 6 ESOs | 6 Signed Contracts with the ESOs. |  | 2025-09-01 | 2025-09-30 | 2025-10-10 |  | In Progress | High
Share frameworks for review with ESOs and Legal team
Signing of the frameworks with the ESOs.
2.1.6.9 | ESO Onboarding and Introduction to incubation and acceleration frameworks (curriculum, due diligence, digital economy integration). | Design orientation package (process framework, digital tools, curriculum guides, reporting templates, Memo). | A master onboarding deck and memo approved by the Program Lead.
|  | Review Onboarding Decks from OUL Work streams. | Workstream presentations approved
|  | Conduct ESO induction workshop on program objectives, delivery model, and performance expectations. Initial on boarding trainings on Safe guarding, Gender, Results Measurement, Communications, Learning Design, Incubation and Acceleration with the contracted ESOs. | Onboarding workshop done
|  | Share standardized tools (reporting templates, MSME selection criteria, MEL framework). | Standardized tools shared
2.1.6.10 | Inception report and Co-design of interventions with outbox | Co-create detailed incubation/acceleration implementation plans with each ESO
Review of the shared Inception reports ensuring that there is alignment with Program goals.
Launch incubation and acceleration cohorts through partner ESOs.
[9 empty] | In Progress | High
2.1.8 | 2.1.8 Deliver the approved digital economy incubator/accelerator initiatives to MSMEs with linkages to digital platform providers, finance and bundled with access to devices. Run women only focused cohorts with a select group of ESOs. Each ESO will deliver at least two incubator/accelerator initiatives per year targeting its community of entrepreneurs.
2.1.8.2 | Roll out of the first and second cohorts by the ESOs to identify the MSMEs to be on boarded for the Acceleration Program. | The calls will launched on the Outbox & partner websites with clear activity timelines. | 21,040 young women in outreach |  | 2025-05-19 | 2026-07-23 |  |  | In Progress | High | This activity was dependent on ESOs being contracted which was delayed and only took place in May, this meant that the activity needed to rolled over
Outbox will support the ESOs to establish a system to track application submissions, engagement metrics, and a report summarizing the outreach efforts, including the number of applications received and initial analysis of applicant quality and diversity. Plan, execute and monitor MSME digitization campaign, including awareness, onboarding, education, and ongoing usage support.
Provide oversight to the ESOs on the identify & selection of suitable businesses as per the agreed criteria to join the first and second cohorts of the accelerator.
Outbox will provide the tools for assessment & evaluation and the independent team for selection of the final businesses. Outbox will also carry out overall QA of the recommended pipeline by the ESOs. Reviewing the course content and updating the learning Management System based on learnings from previous cohorts.
2.1.8.4 | Offer tailored support to the MSMEs based on their Growth plans | ESOs build MSMEs capacity to complete the foundation course. | 14,500 MSMEs have been supported through the Acceleration Program |  | 2025-07-01 | 2026-06-30 |  |  | In Progress | High
|  | Due diligence & needs assessment by ESOs for the MSMEs while maintaining safeguarding guidelines. | 14,728 Youth in Work
ESOs offer tailored support and technical assistance that enables the MSMEs to access digital platforms, credit, market and improved business management practices.
2.1.8.7 | Identify and partner with TVETs with computers that can be used by entrepreneurs for learning | In partnership with Refactory and Outbox, identify TVET institutions with computer labs that can host entrepreneurs for practical DE training. | Serviced IT infrastructure of 6 selected TVETs equipped for MSME digital training |  | 2026-01-01 | 2026-02-27 |  |  | Not Started | Medium | This activity is rolled over to Year 2 was dependent on Refactory identifying TVETS to develop programs after it completed the TVET capacity assessment
Map and assess TVETs with existing IT infrastructure
Engage selected institutions
Confirm availability and readiness for MSME use
Facilitate basic upgrades or support where necessary
2.1.8.8 | Conduct on site progress visits to observe and gather insights on the implemented activities | Throughout the accelerator initiatives, Outbox will carry out quarterly visits to the ESOs and MSMEs to document key insights to inform future accelerators, in collaboration with the accelerators team, RM and communications team at Outbox | 4 Quarterly visits conducted |  | 2025-09-17 | 2026-05-29 |  |  | Not Started | High | This activity was dependent on ESOs being contracted which was delayed and only took place in May, this mean that this activity needed to rolled over after ESOs had completed the first cohort
|  | Best practices, successes and learning in safeguarding, inclusion and disability mainstreaming will captured and documented as learning briefs. | 2 learning briefs that position Outbox as thought leaders
2.1.8.9 | Document success stories, and design and implement MSME digitization campaign (awareness, onboarding, education, usage support) | Plan, execute and monitor MSME digitization campaign, including awareness, onboarding, education, and ongoing usage support. | Success stories |  | 2025-08-13 | 2026-05-29 |  |  | Not Started | High
2.1.8.10 | Conduct Due Diligence & Eligibility Checks for MSMEs | The Outbox team will sample MSMEs from the ESO pipeline for field visits to assess the operational status, validate information provided, and determine their readiness for technical assistance, digital adoption support, market linkage opportunities, or investment readiness interventions. | Actionable insights to support ESO program alignment and MSME support planning |  | 2025-07-07 | 2025-08-30 | 2025-11-14 | The delay in the MSME study procurement affected foundation course development and launch. ESO launched the accelerators in August and the first cohort is expected to end in Oct/Nov. | Not Started | High
2.1.8.11 | ESO Specialized (Advanced level) Curriculum Dissemination. The Outbox team will attend some of the onboarding workshops for ESOs-MSMEs for the Advanced courses | The Outbox team will participate in selected onboarding workshops between ESOs and MSMEs for the Advanced-level courses. This engagement will support the effective dissemination of the specialized curriculum and enable the Outbox team to assist ESOs in tailoring and refining their content based on real-time feedback and context-specific needs. | Tailored advanced curricullum |  | 2025-08-03 | 2025-10-03 |  |  | Not Started | High
2.2.3.3 | Delivery of capacity building sessions to ESOs | Based on the gaps identified by the FMCS during the Due diligence/OCA process, Outbox will undertake to extend support to ESOs on their Service delivery/Capacity improvement plans implemented with initial supervision from the consultant through group trainings and tailored coaching sessions. | Initial report on progress made by each partner vs the planned activities |  | 2025-11-03 | 2026-05-30 |  |  | Not Started | Medium
Outbox will conduct bi-monthly trainings for the ESOs on program delivery components that include Finance, Digital adoption, Learning Design and Results Measurement to ensure alignment with program approach and expectations
2.2.4 | Conduct bi-annual organizational capacity assessment to determine progress made in addressing the weaknesses identified
2.2.4.1 | Conduct validation and follow-ups on consortium partners and ESOs Capacity improvement plans | FMCS Partner carry out validation and follow-ups on consortium partners and ESOs Capacity improvement plans | A capacity improvement report. |  | 2025-12-01 | 2026-06-30 |  |  | Not Started | Medium
2.1.7 | Co-create digital economy incubator/accelerator initiatives with selected ESOs to support participating MSMEs to adopt/integrate the appropriate digital solutions coupled with business support services. Setup structures for bundling of digital devices with business support services, repayment structures for devices. Receive support from Light for the World on disability inclusion aspects. | UNCDF and Outbox will host co-creations workshops with the first cohort of ESOs to develop a go to market strategy for the device financing, digital credit and digital platform providers.
Outbox and UNCDF will facilitate workshops with the selected ESOs to define incubation bundles, including devices and tools; integrate the program device distribution and financing go to market strategy. ESOs will revise their technical models in the incubators/ accelerators that they will implement in the program year in the advanced phase of accelerator.
2.2 | Capacities of 15 ESOs are strengthened and built to deliver appropriate digital skilling and technical assistance to MSMEs, strengthen internal processes that establish additional revenue streams rooted in DE
2.2.2 | Together with participating ESOs, cocreate digital services business models to roll-out or scale to test revenue streams | Outbox will host co-creation workshops in partnership with UNCDF and platform providers with selected ESOs in the program to embed DE business models (device distribution strategy and financing) and support services into their service offering. ESOs test and refine the developed DE business models and support services that enable them create sustainability and revenue streams.
2.2.3.1 | Deliver training and professional development to ESO staff based on the common gaps identified | Outbox will develop and disseminate Terms of Reference to recruit consultants, who will be selected jointly with the Foundation to support ESOs in addressing capacity gaps identified through FMCS due diligence. Outbox will provide ongoing support through tailored coaching, group trainings, and quarterly sessions on program delivery, inclusion, and results measurement.
2.2.4 | The FMCS will conduct bi-annual validation of the capacity improvement plans to determine progress made in addressing the weaknesses identified from the OCA. | FMCS partner will carry out validation and follow-ups on consortium partners and ESOs capacity improvement plans
6.1 | Conduct Monitoring and Evaluation Activities to Support Results Measurement, Tracking, Reporting of the programme.
6.1.2 | Conduct project monitoring visits (quarterly/ bi annually | UNCDF will conduct monitoring visits for its downstream partners - Project Officers Consortium partners will conduct monitoring visits for their individual down stream partners.- Project officers
6.1.2.1 | UNCDF provides input to the design process and content of the impact dashboard as developed by Outbox | Outbox drafts the Impact Dashboard Mockup and shares with UNCDF for review and feedback
UNCDF will provides input to the design process and content of the impact dashboard as developed by Outbox
Outbox will develop the live Impact dashboard with support from UNCDF
6.1.2.4 | Develop a portfolio management system for ESOs | Developing a TOR Shortlisting and selection of consultants Development of user requirements Design of the intended tools Development of the tools
4.2 | Support the design, pilot and rollout of financing and distribution models for access to affordable devices
4.2.3 | Identify promising device lending solutions on the market, provide them with T.A to rethink their models / solutions to better serve the target youth businesses /MSMEs. | Conclude Due diligence on first set of selected grant applicants
Undertake selection process on second set of grant applicants
Undertake due diligence on second set of applicants grant applicants
3.2 6 local digital transformation solutions created for MSMEs | 06 local digital transformation solutions created for MSMEs
3.2.1 | Managing the repayable grant fund for the six startups and Outbox will support with the implementation of the open innovation challenge | Through a call of application, recruit a grant manager to manage the innovation challenge grants
3.2.3 | Select solutions to be supported in the incubation program | With support from UNCDF, the selection committee selects startups to participate in the accelerator programme run by Outbox
Outbox runs the accelerator programme
UNCDF launches grant call - for participants in the accelerator programme to apply
UNCDF in collaboration with Oubox select six emerging startups to receive innovation grants
Outbox and UNCDF provide post accelerator programme technical assistance to the 6 startups
UNCDF disburses performance based grants to the 6 startups
3.1 | Establish partnerships with 3 existing private sector digital platform providers to address the needs of youth led MSMEs
3.1.1 | Through a call for applications, identify platforms on the market that are relevant and appropriate for the MSMEs to access to markets, finance, optimized operations, upskilling, improved customer engagement | Project approval for 3 implementing partners(UNCDF investment committee)
3.1.2 | Engage and sign partnerships with select platforms that exhibit the most value for MSMEs. | Sign performance based agreement with 3 platform providers
Project inception: Work with selected partners to conclude project implementation plans, budgets
Partner induction on program approach to gender, disability and safeguarding and quarterly review assessments on progress on gender, disability and safeguarding. Undertake gender, safeguarding, disability audit
Communication around new platforms onboarded and the value they bring to MSMEs
3.1.3 | Provide technical assistance and innovation grants to selected digital platform providers to improve their platforms / business models and roll them out to the target MSMEs. | Identify capacity needs to deliver on project to inform scope of technical assistance and platform enhancements
Work with Outbox to build awareness around the innovation challenge
3.1.4 | Working with platform providers and ESOs, support MSMEs to adopt the appropriate digital solutions into their operations. | Implement MSME inclusive digitization campaign (awareness, onboarding, education, usage support)

## Events_Calendar
Workstream | Date for the event | Event Title | Location [Venue/Virtual] | Time | Target Audience [Who is attending?] | Objectives [Key goal of event] | Responsible Team [Lead team/person] | Workstreams needed | Procurement and Finance needs
Incubation and Acceleration | 2025-08-20 | Cocreation workshop for ESOs that submitted concept notes | Venue TBD | 8:30 a.m. to 5:00 p.m | ESOs that submitted concept notes. | · To help participants understand the 10X program and what it seeks to achieve in terms of the objectives, pathways to work, impact and the different components · Enable participants understand what is expected of them in their proposals in terms of: impact, intervention design, sustainability, finance, target audience. | Incubator and Accelerator Process Lead | All | Venue and meals
| 2025-09-10 | Follow on co creation between ESOs and platform providers. | Outbox Boardroom | 8:30 a.m. to 5:00 p.m | ESOs Platform providers | To deepen collaboration between Entrepreneurship Support Organisations (ESOs) and platform providers. | Incubator and Accelerator Process Lead | All | Venue and meals
| 2025-09-15 | Due diligence for the second call of ESOs | Western Eastern Northern | 08:00 a.m to 5:00 p.m | ESOs that have been passed the evaluation stage | To assess the operational capacity, governance standards, financial integrity, and strategic alignment of applicant ESOs in order to ensure that selected organisations are capable of delivering high-impact support to entrepreneurs | Incubation and Acceleration Lead and the Partner Success Lead | All | Car, fuel, accomodation and per diem
| 2025-09-30 | Negotiations with ESOs that have passed the due diligence stage | Outbox Boardroom | 08:00 a.m to 5:00 p.m | ESOs that have passed the due diligence stage | Clarify the ESO’s role, target outcomes, and support mechanisms and align on budget allocations, staffing, and infrastructure readiness. | Incubation and Acceleration Lead, | Finance Lead and the Partner Success Lead | Meals
| 2025-10-01 | ESO Onboarding | Western Eastern Northern | 08:00 a.m to 5:00 p.m | ESOs that have signed contracts | To equip selected Entrepreneurship Support Organisations (ESOs) with the necessary tools, knowledge, and alignment to effectively implement the | Incubation and Acceleration Lead | All | Venue, meals
| 2025-10-06 | Inception report discussions | Kampala (TBD) | 08:00 a.m to 5:00 p.m | ESOs that have signed contracts | To ensure alignment with each ESO, ensuring that they understand what the programme is all about, and that their proposed plan is both practical and aligned with our shared goals. | Incubation and Acceleration Lead | All | Venue, meals
| 2025-09-23 | Pause and Reflect with all ESOs | Kampala (TBD) | 08:00 a.m to 5:00 p.m | The first signed 8 ESOs | To create a dedicated space for ESOs to step back from day-to-day implementation, share experiences, and collectively reflect on progress, challenges, and lessons learned. | Incubation and Acceleration Lead | All | Venue, meals
Communications | 2025-09-11 | 10X Program ESOs Comms Capacity Building Session | Online | 9:00 am to 11:00 a.m | Comms leads for ESOs | 1. Build a shared understanding of 10X Program communications priorities – Ensure all partners are aligned on the program’s core messages, safeguarding language, and inclusive framing. 2. Enhance consistency and visibility of the 10X Program – Establish clear guidelines for branding, social media use, and reporting to ensure coherence across all communication channels. 3. Foster knowledge exchange – Provide a platform for partners to share best practices, challenges, and innovative communication approaches from their contexts. | Violet Nakiggwe. Comms Lead
| 2025-09-15 | Review of Outbox safeguarding assessment tool | TBD | 8:30 am to 5:00 pm | Selected staff | Work with IIDC on the updated safeguarding assessment | Rahmah Nampala | Selected
| 2025-09-18 | Disability Inclusion Training for all 10X program staff | TBD | 8:30 am to 5:00 pm | All partner staff and their downstream partners |  | Rahmah Nampala | All
| 2025-09-19 | Disability Inclusion Training for all 10X program staff | TBD | 8:30 am to 5:00 pm | All partner staff and their downstream partners |  | Rahmah Nampala | All
| 2025-09-23 | Disability Inclusion Training for all 10X program staff | TBD | 8:30 am to 5:00 pm | All partner staff and their downstream partners |  | Rahmah Nampala | All
| 2025-09-24 | Disability Inclusion Training for all 10X program staff | TBD | 8:30 am to 5:00 pm | All partner staff and their downstream partners |  | Rahmah Nampala | All
| 2025-09-25 | 10X Inclusion Community of Practice meeting | TBD | 8:30 am to 5:00 pm | Gender focal persons |  | Rahmah Nampala | Gender unit
Learning Workstream | 2025-09-26 | Review of the 10X Program Specialized and accelerator curriculum | Kampala (TBD) | 8:30 am to 5:00 pm | ESO focal persons & Learning teams | ESO Specialized Curriculum review | Valerie Kyolaba | Partner Success Lead, Accelerator & Process Lead | Venue and meals

## ESO_Outreach
ESO NAME | Tasks | Assigned To | Start | End | Days | Status | Duration | Deliverable | District/Location | Lead name | contact
MUBS-EIIC_ESO OUTREACH CALENDAR ENDING | Project Kick-off+Staff Recruitment+TOTs | Sarah Kyejjusa/ Dr. Diana Ntamu | 2025-08-25 | 2025-09-12 | 18 | Not Started | -18 | Direct + Indirect staff recruited, Trained and oriented to the program | Mbale City | Sarah Kyejjusa/ Dr. Diana Ntamu | Phone: +256 772 454602 Email: skyejjusa@mubs.ac.ug
MUBS-EIIC_ESO OUTREACH CALENDAR ENDING | Community takeholder engagement | Rehema Namutangula/Charles Olupot | 2025-09-01 | 2025-09-12 | 11 | Not Started | -11 | Community clearance and authorization to engage with the community | Nakapiripirit, Kapchorwa, Kween, Tororo, Busia, Sironko and Mbale City | Rehema Namutangula/Charles Olupot | Phone: +256 772 323230 Email: karemmie@mubs.ac.ug
MUBS-EIIC_ESO OUTREACH CALENDAR ENDING | Participant Mobilization & MSME Onboarding | Rehema Namutangula / TBD | 2025-09-01 | 2025-09-30 | 29 | Not Started | -29 | 2500 young women on boarded | Nakapiripirit, Kapchorwa, Kween, Tororo, Busia, Sironko and Mbale City | Rehema Namutangula / TBD | Phone: +256 772 323230 Email: karemmie@mubs.ac.ug
MUBS-EIIC_ESO OUTREACH CALENDAR ENDING | Digital Profiling & Baseline Assessment | Charles Olupot/Mable Kemigisha/Rehema Namutangula | 2025-09-01 | 2025-09-30 | 29 | Not Started | -29 | Digital readiness of MSMEs assessed | Nakapiripirit, Kapchorwa, Kween, Tororo, Busia, Sironko and Mbale City | Charles Olupot/Mable Kemigisha/Rehema Namutangula | Phone: +256 704743039 Email: olupot@mubs.ac.ug
MUBS-EIIC_ESO OUTREACH CALENDAR ENDING | Foundational Course Training & Handholding | Mable Kemigisha/Charles Olupot/Rehema Namutangula | 2025-09-01 | 2025-10-24 | 53 | Not Started | -53 | Foundational training delivered to 500 MSMEs | Nakapiripirit, Kapchorwa, Kween, Tororo, Busia, Sironko and Mbale City | Mable Kemigisha/Charles Olupot/Rehema Namutangula | Phone: +256 774 330137 Email: mkemigisha@mubs.ac.ug
MUBS-EIIC_ESO OUTREACH CALENDAR ENDING | Due Diligence & Selection of 500 MSMEs | Sarah Kyejjusa/Charles Olupot | 2025-09-15 | 2025-10-24 | 39 | Not Started | -39 | 500 MSMEs selected for tailored support | Nakapiripirit, Kapchorwa, Kween, Tororo, Busia, Sironko and Mbale City | Sarah Kyejjusa/Charles Olupot | Phone: +256 772 454602 Email: skyejjusa@mubs.ac.ug
MUBS-EIIC_ESO OUTREACH CALENDAR ENDING | Orientation to Tailored BDS Tracks | Sarah Kyejjusa/Dr. Diana Ntamu/Charles Olupot/Rehema Namutangula | 2025-10-27 | 2025-10-31 | 4 | Not Started | -4 | MSMEs oriented to BDS tracks | Nakapiripirit, Kapchorwa, Kween, Tororo, Busia, Sironko and Mbale City | Sarah Kyejjusa/Dr. Diana Ntamu/Charles Olupot/Rehema Namutangula | Phone: +256 772 454602 Email: skyejjusa@mubs.ac.ug
MUBS-EIIC_ESO OUTREACH CALENDAR ENDING | BDS Training: Business Efficiency | Sarah Kyejjusa/Charles Olupot/Rehema namutangula | 2025-11-03 | 2025-11-28 | 25 | Not Started | -25 | Efficiency module completed | Nakapiripirit, Kapchorwa, Kween, Tororo, Busia, Sironko and Mbale City | Sarah Kyejjusa/Charles Olupot/Rehema namutangula | Phone: +256 772 454602 Email: skyejjusa@mubs.ac.ug
MUBS-EIIC_ESO OUTREACH CALENDAR ENDING | BDS Training: Market Readiness | Sarah Kyejjusa/Charles Olupot/Rehema Namutangula/TBD | 2025-11-03 | 2025-11-28 | 25 | Not Started | -25 | Market access module completed | Nakapiripirit, Kapchorwa, Kween, Tororo, Busia, Sironko and Mbale City | Sarah Kyejjusa/Charles Olupot/Rehema Namutangula/TBD | Phone: +256 772 454602 Email: skyejjusa@mubs.ac.ug
MUBS-EIIC_ESO OUTREACH CALENDAR ENDING | BDS Training: Investment Readiness & Digital Credit | Sarah Kyejjusa/Charles Olupot/Rehema Namutangula/TBD | 2025-11-03 | 2025-11-28 | 25 | Not Started | -25 | Investment readiness module completed | Nakapiripirit, Kapchorwa, Kween, Tororo, Busia, Sironko and Mbale City | Sarah Kyejjusa/Charles Olupot/Rehema Namutangula/TBD | Phone: +256 772 454602 Email: skyejjusa@mubs.ac.ug
MUBS-EIIC_ESO OUTREACH CALENDAR ENDING | One-on-One Mentorship & Coaching | Sarah Kyejjusa/Charles Olupot/Rehema Namutangula/TBD | 2025-12-01 | 2025-12-20 | 19 | Not Started | -19 | Personalized mentorship completed | Nakapiripirit, Kapchorwa, Kween, Tororo, Busia, Sironko and Mbale City | Sarah Kyejjusa/Charles Olupot/Rehema Namutangula/TBD | Phone: +256 772 454602 Email: skyejjusa@mubs.ac.ug
MUBS-EIIC_ESO OUTREACH CALENDAR ENDING | B2B Engagement Forums | Sarah Kyejjusa/Dr. Diana Ntamu/Charles Olupot/Rehema Namutangula | 2025-12-01 | 2025-12-20 | 19 | Not Started | -19 | Partnerships with tech/fintech providers | Nakapiripirit, Kapchorwa, Kween, Tororo, Busia, Sironko and Mbale City | Sarah Kyejjusa/Dr. Diana Ntamu/Charles Olupot/Rehema Namutangula | Phone: +256 772 454602 Email: skyejjusa@mubs.ac.ug
MKAZIPRENEUR (SOCIAL ENTERPRISE) LTD | Foundational Course Training & Handholding | Sarah Nandudu | 2025-08-20 | 2025-08-20 | 0 | Not Started | 0 | Foundational Course completion support | Malongwe Library Ajiija | Sarah Nandudu | 783516106
MKAZIPRENEUR (SOCIAL ENTERPRISE) LTD | Foundational Course Training & Handholding | Sarah Nandudu | 2025-08-20 | 2025-08-20 | 0 | Not Started | 0 | Foundational Course completion support | Kisaara Vocational Training center | Sarah Nandudu | 783516106
MKAZIPRENEUR (SOCIAL ENTERPRISE) LTD | Foundational Course Training & Handholding | Sarah Nandudu | 2025-08-20 | 2025-08-20 | 0 | Not Started | 0 | Foundational Course completion support | Lugazi central market | Sarah Nandudu | 783516106
MKAZIPRENEUR (SOCIAL ENTERPRISE) LTD | Foundational Course Training & Handholding | Sarah Nandudu | 2025-08-21 | 2025-08-21 | 0 | Not Started | 0 | Foundational Course completion support | St luke vocational institute | Sarah Nandudu | 783516106
MKAZIPRENEUR (SOCIAL ENTERPRISE) LTD | Foundational Course Training & Handholding | Sarah Nandudu | 2025-08-21 | 2025-08-21 | 0 | Not Started | 0 | Foundational Course completion support | Hope Christian school - Nakibole community | Sarah Nandudu | 783516106
MKAZIPRENEUR (SOCIAL ENTERPRISE) LTD | Foundational Course Training & Handholding | Deborah Amulen | 2025-08-27 | 2025-08-27 | 0 | Not Started | 0 | Foundational Course completion support | Learning field visit at UIRI | Deborah Amulen | 783141758
MKAZIPRENEUR (SOCIAL ENTERPRISE) LTD | Foundational Course Training & Handholding | Deborah Amulen | 2025-08-29 | 2025-08-29 | 0 | Not Started | 0 | Foundational Course completion support | Networking Friday at Mkazi hub in Ntinda | Deborah Amulen | 783141758
MKAZIPRENEUR (SOCIAL ENTERPRISE) LTD | Foundational Course Training & Handholding | Sarah Nandudu | 2025-08-30 | 2025-08-30 | 0 | Not Started | 0 | Foundational Course completion support | Bar soap making skilling session at Mkazi Hub in Ntinda | Sarah Nandudu | 783516106
MKAZIPRENEUR (SOCIAL ENTERPRISE) LTD | Foundational Course Training & Handholding | Sarah Nandudu | 2025-08-27 | 2025-08-28 | 1 | Not Started | -1 | Foundational Course completion support | Outreaches in the refugee areas of kibuli and Kansanga | Sarah Nandudu | 783516106
MKAZIPRENEUR (SOCIAL ENTERPRISE) LTD | Foundational Course Training & Handholding | Sarah Nandudu | 2025-09-08 | 2025-09-12 | 4 | Not Started | -4 | Foundational Course completion support | Course completion bootcamp at Lugazi market | Sarah Nandudu | 783516106
MKAZIPRENEUR (SOCIAL ENTERPRISE) LTD | Foundational Course Training & Handholding | Sarah Nandudu | 2025-09-15 | 2025-09-19 | 4 | Not Started | -4 | Foundational Course completion support | Mukono district outreaches | Sarah Nandudu | 783516106
SBIL | Pre Inception, stakeholder engagements | Anthea Ankunda | 2025-08-25 | 2025-08-30 | 5 | Not Started | -5 | Pre Inception, stakeholder engagements | Luweero, Nakaseke, Nakasongola, Kiboga Buikwe, Wakiso & Mukono | Anthea Ankunda | 773109935
SBIL | Training of Trainers/ Learning Champions | Amos Baguma | 2025-09-08 | 2025-09-09 | 1 | Not Started | -1 | Training of Trainers/ Learning Champions | Kampala | Amos Baguma | 750810926
SBIL | Learning Champions will run individual group or one on one sessions to onboard Learners/MSMEs | Amos Baguma | 2025-09-10 | 2025-09-30 | 20 | Not Started | -20 | Learning Champions will run individual group or one on one sessions to onboard Learners/MSMEs | Luweero, Nakaseke, Nakasongola, Kiboga Buikwe, Wakiso & Mukono, Kampala | Amos Baguma | 750810926
SBIL | Official District Inception meeting to introduce the program to all relevant district stakeholders | Anthea Ankunda | 2025-09-11 | 2025-09-11 | 0 | Not Started | 0 | Official District Inception meeting to introduce the program to all relevant district stakeholders | Nakasongola | Anthea Ankunda | 773109935
SBIL | Official District Inception meetings to introduce the program to all relevant district stakeholders | Anthea Ankunda | 2025-09-17 | 2025-09-17 | 0 | Not Started | 0 | Official District Inception meetings to introduce the program to all relevant district stakeholders | Luwero | Anthea Ankunda | 773109935
SBIL | Official District Inception meetings to introduce the program to all relevant district stakeholders | Anthea Ankunda | 2025-09-18 | 2025-09-18 | 0 | Not Started | 0 | Official District Inception meetings to introduce the program to all relevant district stakeholders | Nakaseke | Anthea Ankunda | 773109935
SBIL | Official District Inception meetings to introduce the program to all relevant district stakeholders | Anthea Ankunda | 2025-09-22 | 2025-09-22 | 0 | Not Started | 0 | Official District Inception meetings to introduce the program to all relevant district stakeholders | Kiboga | Anthea Ankunda | 773109935
SBIL | Official District Inception meetings to introduce the program to all relevant district stakeholders | Anthea Ankunda | 2025-09-24 | 2025-09-24 | 0 | Not Started | 0 | Official District Inception meetings to introduce the program to all relevant district stakeholders | Wakiso | Anthea Ankunda | 773109935
SBIL | Official District Inception meetings to introduce the program to all relevant district stakeholders | Anthea Ankunda | 2025-09-26 | 2025-09-26 | 0 | Not Started | 0 | Official District Inception meetings to introduce the program to all relevant district stakeholders | Buikwe | Anthea Ankunda | 773109935
SBIL | Official District Inception meetings to introduce the program to all relevant district stakeholders | Anthea Ankunda | 2025-09-28 | 2025-09-28 | 0 | Not Started | 0 | Official District Inception meetings to introduce the program to all relevant district stakeholders | Mukono | Anthea Ankunda | 773109935
dfcu foundation | Foundational Course onboarding & MSME Capacity Assessments | Daniel Ikaaba | 2025-09-16 | 2025-09-16 | 0 | Not Started | 0 | Foundational Course onboarding & MSME Capacity Assessments | Bulambuli | Daniel Ikaaba | 784264444
dfcu foundation | Foundational Course onboarding & MSME Capacity Assessments | William Ssenyondo | 2025-09-16 | 2025-09-16 | 0 | Not Started | 0 | Foundational Course onboarding & MSME Capacity Assessments | Paliisa | William Ssenyondo | 700123076
dfcu foundation | Foundational Course onboarding & MSME Capacity Assessments | Simon Omara | 2025-09-16 | 2025-09-16 | 0 | Not Started | 0 | Foundational Course onboarding & MSME Capacity Assessments | Tororo | Simon Omara | 705590564
dfcu foundation | Foundational Course onboarding & MSME Capacity Assessments | William Ssenyondo | 2025-09-17 | 2025-09-17 | 0 | Not Started | 0 | Foundational Course onboarding & MSME Capacity Assessments | Budaka | William Ssenyondo
dfcu foundation | Foundational Course onboarding & MSME Capacity Assessments | Simon Omara | 2025-09-17 | 2025-09-17 | 0 | Not Started | 0 | Foundational Course onboarding & MSME Capacity Assessments | Kibuku | Simon Omara
dfcu foundation | Foundational Course onboarding & MSME Capacity Assessments | Daniel Ikaaba | 2025-09-17 | 2025-09-17 | 0 | Not Started | 0 | Foundational Course onboarding & MSME Capacity Assessments | Mbale | Daniel Ikaaba
dfcu foundation | Foundational Course onboarding & MSME Capacity Assessments | William Ssenyondo | 2025-09-19 | 2025-09-19 | 0 | Not Started | 0 | Foundational Course onboarding & MSME Capacity Assessments | Butaleja | William Ssenyondo
dfcu foundation | Foundational Course onboarding & MSME Capacity Assessments | Daniel Ikaaba | 2025-09-19 | 2025-09-19 | 0 | Not Started | 0 | Foundational Course onboarding & MSME Capacity Assessments | Mbale | Daniel Ikaaba
dfcu foundation | Foundational Course onboarding & MSME Capacity Assessments | Simon Omara | 2025-09-19 | 2025-09-19 | 0 | Not Started | 0 | Foundational Course onboarding & MSME Capacity Assessments | Busia | Simon Omara
dfcu foundation | Foundational Course onboarding & MSME Capacity Assessments | Daniel Ikaaba | 2025-09-22 | 2025-09-22 | 0 | Not Started | 0 | Foundational Course onboarding & MSME Capacity Assessments | Nakapiripirit | Daniel Ikaaba
dfcu foundation | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | Daniel Ikaaba | 2025-10-13 | 2025-10-15 | 2 | Not Started | -2 | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | Bulambuli | Daniel Ikaaba | 784264444
dfcu foundation | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | William Ssenyondo | 2025-10-13 | 2025-10-15 | 2 | Not Started | -2 | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | Paliisa | William Ssenyondo | 700123076
dfcu foundation | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | Simon Omara | 2025-10-13 | 2025-10-15 | 2 | Not Started | -2 | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | Tororo | Simon Omara | 705590564
dfcu foundation | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | William Ssenyondo | 2025-10-15 | 2025-10-18 | 3 | Not Started | -3 | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | Budaka | William Ssenyondo
dfcu foundation | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | Simon Omara | 2025-10-16 | 2025-10-18 | 2 | Not Started | -2 | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | Kibuku | Simon Omara
dfcu foundation | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | Daniel Ikaaba | 2025-10-16 | 2025-10-18 | 2 | Not Started | -2 | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | Mbale | Daniel Ikaaba
dfcu foundation | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | William Ssenyondo | 2025-10-20 | 2025-10-22 | 2 | Not Started | -2 | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | Butaleja | William Ssenyondo
dfcu foundation | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | Simon Omara | 2025-10-20 | 2025-10-22 | 2 | Not Started | -2 | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | Busia | Simon Omara
dfcu foundation | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | Daniel Ikaaba | 2025-10-20 | 2025-10-22 | 2 | Not Started | -2 | Workshops in Governance, Regulatory & Digital Literacy (Cohorts 1 & 2) | Nakapiripirit | Daniel Ikaaba
dfcu foundation | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | Daniel Ikaaba | 2025-11-17 | 2025-11-19 | 2 | Not Started | -2 | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | Bulambuli | Daniel Ikaaba | 784264444
dfcu foundation | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | William Ssenyondo | 2025-11-17 | 2025-11-19 | 2 | Not Started | -2 | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | Paliisa | William Ssenyondo | 700123076
dfcu foundation | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | Simon Omara | 2025-11-17 | 2025-11-19 | 2 | Not Started | -2 | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | Tororo | Simon Omara | 705590564
dfcu foundation | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | William Ssenyondo | 2025-11-20 | 2025-11-22 | 2 | Not Started | -2 | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | Budaka | William Ssenyondo
dfcu foundation | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | Simon Omara | 2025-11-20 | 2025-11-22 | 2 | Not Started | -2 | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | Kibuku | Simon Omara
dfcu foundation | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | Daniel Ikaaba | 2025-11-20 | 2025-11-22 | 2 | Not Started | -2 | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | Mbale | Daniel Ikaaba
dfcu foundation | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | William Ssenyondo | 2025-11-24 | 2025-11-26 | 2 | Not Started | -2 | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | Butaleja | William Ssenyondo
dfcu foundation | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | Simon Omara | 2025-11-24 | 2025-11-26 | 2 | Not Started | -2 | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | Busia | Simon Omara
dfcu foundation | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | Daniel Ikaaba | 2025-11-24 | 2025-11-26 | 2 | Not Started | -2 | Capacity Strengthening Workshops for MSMEs in Device Financing and Hands-on training on Digital Tools (Cohort 1&2) | Nakapiripirit | Daniel Ikaaba
PEDN | Call for Application to join the PEDN 10X Program | Joy Mukisa Michael Kawagga | 2025-06-30 | 2025-09-12 | 74 | Not Started | -74 | Call for Application to join the PEDN 10X Program | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | 10X Digital Foundation Course Evaluate and shortlist atleast 3,000 Young women Atleast 600 MSMEs graduate | Joy Mukisa Michael Kawagga | 2025-08-15 | 2025-09-15 | 31 | Not Started | -31 | 10X Digital Foundation Course Evaluate and shortlist atleast 3,000 Young women Atleast 600 MSMEs graduate | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | Due diligence and needs assessment of the MSMEs, select 500MSMEs Sign EoI & contracts and develop a clear growth plan for each of 500 MSMEs | Joy Mukisa Michael Kawagga | 2025-08-22 | 2025-09-22 | 31 | Not Started | -31 | Due diligence and needs assessment of the MSMEs, select 500MSMEs Sign EoI & contracts and develop a clear growth plan for each of 500 MSMEs | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | Meeting with regulatory bodies for guidance on compliance, product quality or certification (UIRI, URA,URSB, UNBS, NSSF, etc) ONLINE | Joy Mukisa Michael Kawagga | 2025-09-15 | 2025-09-15 | 0 | Not Started | 0 | Meeting with regulatory bodies for guidance on compliance, product quality or certification (UIRI, URA,URSB, UNBS, NSSF, etc) ONLINE | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | Radio mentions Awareness campaigns - On financial management and digital credit | Joy Mukisa Michael Kawagga | 2025-10-06 | 2025-10-15 | 9 | Not Started | -9 | Radio mentions Awareness campaigns - On financial management and digital credit | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | Radio Talkshows / Mobilizing participants Awareness - On financial management and digital credit | Joy Mukisa Michael Kawagga | 2025-10-07 | 2025-10-07 | 0 | Not Started | 0 | Radio Talkshows / Mobilizing participants Awareness - On financial management and digital credit | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | Community meetings Awareness campaigns - On financial management and digital credit | Joy Mukisa Michael Kawagga | 2025-10-08 | 2025-10-08 | 0 | Not Started | 0 | Community meetings Awareness campaigns - On financial management and digital credit | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | Workshop 1 (on Financial Management, Digital Credit & GESI) | Joy Mukisa Michael Kawagga | 2025-10-14 | 2025-10-14 | 0 | Not Started | 0 | Workshop 1 (on Financial Management, Digital Credit & GESI) | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | Technical one-on-one support to MSMEs Visits to the MSMEs | Joy Mukisa Michael Kawagga | 2025-10-15 | 2025-10-27 | 12 | Not Started | -12 | Technical one-on-one support to MSMEs Visits to the MSMEs | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | Refresher workshop (ONLINE) on Financial Management and Digital Credit | Joy Mukisa Michael Kawagga | 2025-10-21 | 2025-10-21 | 0 | Not Started | 0 | Refresher workshop (ONLINE) on Financial Management and Digital Credit | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | Workshop 2 (on Digital Devices & GESI) | Joy Mukisa Michael Kawagga | 2025-10-28 | 2025-10-28 | 0 | Not Started | 0 | Workshop 2 (on Digital Devices & GESI) | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | Technical one-on-one support to MSMEs Visits to the MSMEs | Joy Mukisa Michael Kawagga | 2025-10-29 | 2025-11-03 | 5 | Not Started | -5 | Technical one-on-one support to MSMEs Visits to the MSMEs | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | Bootcamps and Pitch days - Cohort 1 | Joy Mukisa Michael Kawagga | 2025-11-04 | 2025-11-06 | 2 | Not Started | -2 | Bootcamps and Pitch days - Cohort 1 | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | B2B Meetings - Cohort 1 | Joy Mukisa Michael Kawagga | 2025-11-12 | 2025-11-12 | 0 | Not Started | 0 | B2B Meetings - Cohort 1 | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | Bootcamps and Pitch days - Cohort 2 | Joy Mukisa Michael Kawagga | 2025-11-25 | 2025-11-27 | 2 | Not Started | -2 | Bootcamps and Pitch days - Cohort 2 | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | Workshop 3 (on Digital Platforms) | Joy Mukisa Michael Kawagga | 2025-12-04 | 2025-12-04 | 0 | Not Started | 0 | Workshop 3 (on Digital Platforms) | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | Technical one-on-one support to MSMEs Visits to the MSMEs | Joy Mukisa Michael Kawagga | 2025-12-05 | 2025-12-12 | 7 | Not Started | -7 | Technical one-on-one support to MSMEs Visits to the MSMEs | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | Community Meeting Awareness on - Digital Platforms | Joy Mukisa Michael Kawagga | 2025-12-08 | 2025-12-08 | 0 | Not Started | 0 | Community Meeting Awareness on - Digital Platforms | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | Radio mentions Awareness on - Digital Platforms | Joy Mukisa Michael Kawagga | 2025-12-01 | 2025-12-10 | 9 | Not Started | -9 | Radio mentions Awareness on - Digital Platforms | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | Radio Talkshows Awareness on - Digital Platforms | Joy Mukisa Michael Kawagga | 2025-12-08 | 2025-12-08 | 0 | Not Started | 0 | Radio Talkshows Awareness on - Digital Platforms | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org
PEDN | B2B Meetings - Cohort 2 | Joy Mukisa Michael Kawagga | 2025-12-15 | 2025-12-15 | 0 | Not Started | 0 | B2B Meetings - Cohort 2 | Busia, Tororo, Mbale, Pallisa, Sironko, Bulambuli, Kapchorwa | Joy Mukisa Michael Kawagga | joy@pedn.org kawagga@pedn.org